Harworth Meeting Notes

11 July 2013

Present Natalie Cockrell and Helen Metcalfe

1. Funding
	* Funding has been obtained from locality to pay for the following
		+ Affordable housing study
		+ Paying for village hall events
		+ Design work and consultation
		+ Printing of the plan
	* An award for All application has been completed to gain funding for design work from OPUN and consultation work from HM.
		+ Awaiting quotes from OPUN and HM
2. Emails/make contact
	* NC to email Steve and June to ensure more people have been recruited onto the steering group.
	* NC to email Mark Willet from the Selby park Academy and invite him to the training event on Wednesday
	* NC to email all primary schools to gauge interest in being part of a school event on the NP to take place in September/October.
	* NC to contact youth centre
	* NC to speak to secondary school about super learning days
3. Maps
	* A4 blank maps of each site in Harworth containing ownership details.
	* A1 base map just showing the settlement
	* A1 map showing all current permissions and local plan allocations
	* A1 map of all SHLAA sites and SHLAA extracts for each site
	* Print timeline A2
4. Project Plan

Issues and options Consultation – August 2014 onwards

* Opening of the pond with the schools – NC & HM to attend the 3 primary schools (children in YR 5/6) to carry out a session in the morning and visit to the pond in the afternoon
* Competition with the children
* Pop up shop in Harworth to open in October
* NC- to carry out consultation in the summer holidays with the Youth Centre and send out flyer
* Cinema afternoon at the Town Hall and Consultation
* Secondary school event
* Planning over a pint at Blacksmith Arms
* Face to Face visits at the retail shops to discuss the project and promote
* Community event – tag onto something or organise a x mas fare
* NC to undertake discussions with landowners/developers explain process and seek any financial help with designing of sites?

Evidence base – August 2013 onward

* Review of the evidence base
* Census data
* Need for Town SHLAA assessment (look at Cuckfields PHLAA)

Policy Development - January 2014 onwards

* NC and steering group to start policy development to start after Christmas

Draft Plan and Ideas for Action – April 2014

* Public consultation events
* Secondary school event

Consultation on the draft plan – June

* Start consult on the draft the plan

Amendments to the draft – late July

* NC to write the consultation document
* NC to amend the draft document

Submission to Bassetlaw DC – October 2013

1. Website
	* NC to work on content